## Sheet1
Min
Date | Ref | Item | ACTION | OUTCOME | DEADLINE | BY
13.06.17 |  | Website | Awaiting contact details & photos from councillors | Host requested to update the website |  | GG
| 16/11/56.1 | LB Mapping | Letter sent to WC regarding errors on map | 13.02.18 No Progress from WC |  | AJ
13.06.17 | 17/04/39.1 | Community Resilience Plan | New format rec'd from WC | SB to address |  | SB
14.02.17 | 16/16/76 | Traffic Calming | Meeting with Martin Rose on site | Agenda Item
13.06.17 | 17/02/37 | Neighbourhood Plan | Questionnaire to be circulated to residents | Subject for APM on 9.05.18 Agenda Item |  | VC/SB/AS
13.06.17 | 17/02/39.1 | Community Asset Register | Completion of Land Registry paperwork | MC awaiting response from WC |  | MC
13.06.17 | x | Challows Lane footpath | Overgrown and fence still down | No action undertaken by Mr Toogood |  | GG
12.09.17 | 17/08/62.4 | Telephone Box Slaughterford | Needs Repainting | Sent photo with box # & address to |  | GG
|  |  | Awaiting response from BT | customer.serv.payphones@bt.com
12.0917 | 17/08/62.4 | Snow Plan | 2nd Warden for each area to be appointed | VC to request discretionary funding from WC |  | SB/VC
17.12.17 | 17//92.3 | BT Pole | FTTP CMK V33 5N 50 submission for repositioning | No response |  | GG
17.12.17 | 17/119 | Corporate Planning | 3yr Business Plan for BSPC | Agenda Item |  | ALL
17.12.17 | 17/117.7 | Bybrook Floodplan | Consultation with Colerne Parish Re Paper Mill | Agenda Item |  | AW
Draft Plant
|  | Best Kept Village | Entry forms to be submitted | Website to be updated |  | AJ