## Sheet1
Min
Date | Ref | Item | ACTION | OUTCOME | DEADLINE | BY
13.06.17 |  | Website | Awaiting contact details & photos from councillors |  |  | ALL
| 16/11/56.1 | LB Mapping | Letter sent to WC regarding errors on map | No further information available from WC |  | AJ
13.06.17 | 17/04/39.1 | Community Resilience Plan | New format rec'd from WC | SB Lead |  | SB
14.02.17 | 16/16/76 | Traffic Calming | With CATG | Agenda Item
13.06.17 | 17/02/37 | Neighbourhood Plan | Subject for Annual Parish Meeting? | Open mtg 15.01.18 Agenda Item |  | VC/SB/AS
13.06.17 | 17/02/39.1 | Community Asset Register | Completion of Land Registry paperwork |  |  | MC
13.06.17 | x | Challows Lane | Overgrown and fence still down | No action undertaken by Mr Toogood |  | GG
12.09.17 | 17/08/62.4 | Telephone Box Slaughterford | Needs Repainting | Sent photo with box # & address to |  | GG
customer.serv.payphones@bt.com
12.0917 | 17/08/62.4 | Snow Plan | Condition of Grit Boxes and order for salt done | SB to bring Snow Plan up to date and advise Weather Team |  | SB
17.12.17 | 17//92.3 | BT Pole | BT to be requested position of pole within hedge | FTTP CMK V33 5N 50 submission for repositioning sent |  | GG
17.12.17 | 17/94.6 | Corporate Planning | Workshop 8.01.18 | Agenda Item |  | ALL
17.12.17 | 17/94.7 | Bybrook Floodplan | AW writing plan | Agenda Item |  | AW