## Sheet1
Min
Date | Ref | Item | ACTION | OUTCOME | DEADLINE | BY
13.06.17 |  | Website | Awaiting contact details & photos from councillors |  |  | ALL
| 16/11/56.1 | LB Mapping | Letter sent to WC regarding errors on map | No further information available from WC |  | AJ
13.06.17 | 17/04/39.1 | Community Resilience Plan | New format rec'd from WC | SB Lead |  | SB
14.02.17 | 16/16/76 | Traffic Calming | CD Report to all Cllrs | P.Bollen sent Report, engineer to inspect &
| 16/18/90 |  | Request engineer from WC Highways inspect | report back. MC Lead, AS & JS to support |  | MC
13.06.17 | 17/02/38 |  | Clerk to chase. | No response from M Rose 01225 713476 | now with | GG
|  |  | WC requested CATG issue sheets to be raised | Clerk to explain Council needs advice first on best way | CATG | GG
forward.
13.06.17 | 17/02/37 | Neighbourhood Plan | Organise date in Sept for Open Mtg. | 13th Sept Booked | Agenda | VC/SB/AS
| 17/08/55.1 |  | GG to engage a Speaker. | Jane Mellett (Colerne NP) & Nick Stevens (Freshford NP) | Item | GG
|  |  | Meeting arranged 31st October | To form Steering Group |  | SM/VC
13.06.17 | 17/02/39.1 | Community Asset Register | Completion of Land Registry paperwork | MC volunteer to take over from Clerk. |  | MC
| 17/09 /68.4 |  | and registration with WC | Clerk to copy PC Mins ref Cmty Assets List to MC |  | GG
13.06.17 | x | Challows Lane | Overgrown and fence down | DW cleared path/ GG met Mr Toogood who agreed to |  | DW/GG
either remove or replace/repair fence - no date given.
|  |  |  | Clerk to write to Mr Toogood for date when work will be done. |  | GG
12.09.17 | 17/08/62.4 | Telephone Box Slaughterford | Needs Repainting | Send photo with box # & address to |  | RdeF
customer.serv.payphones@bt.com
12.0917 | 17/08/62.4 | Snow Plan | Condition of Grit Boxes and order for salt | SB to bring Snow Plan up to date and advise Weather Team |  | SB