## Sheet1
Min
Date | Ref | Item | ACTION | OUTCOME | DEADLINE | BY
13.06.17 |  | Website | Awaiting contact details & photos from councillors |  |  | ALL
| 16/11/56.1 | Building Regulations | Letter sent to WC regarding errors on map | No further information available from WC |  | AJ
13.06.17 | 17/04/39.1 | Community Resilience Plan | New format rec'd from WC | SB Lead |  | SB
14.02.17 | 16/16/76 | Traffic Calming | CD Report to all Cllrs | P.Bollen sent Report, engineer to inspect &
| 16/18/90 |  | Request engineer from WC Highways inspect | report back. MC Lead, AS & JS to support |  | MC
13.06.17 | 17/02/38 |  | Clerk to chase. | No response from M Rose 01225 713476
13.06.17 | 17/02/37 | Neighbourhood Plan | Organise date in Sept for Open Mtg. | 13th Sept Booked | Agenda | VC/SB/AS
| 17/08/55.1 |  | GG to engage a Speaker. | Jane Mellett (Colerne NP) & Nick Stevens (Freshford NP) | Item | GG
13.06.17 | 17/02/39.1 | Community Asset Register | Completion of Land Registry paperwork and registration | MC volunteer to take over from Clerk. |  | MC
with WC
13.06.17 | x | Challows Lane | Overgrown and fence down | DW cleared path/ GG met Mr Toogood who agreed to |  | DW/GG
either remove or replace/repair fence - no date given.
| 17/08/62.4 | Grit Bin Slaughterford | Needs Replacing | Salt 1 x Ton & survey all bins for Snow Plan by Oct |  | SM
| 17/08/62.4 | Telephone Box Slaughterford | Needs Repainting | Send photo with box # & address to |  | GG
customer.serv.payphones@bt.com